## Other
ID | Due Date | Description | Last Update | Source | Summary Action | Status | Person | Findings
O16 |  | Dana mentioned there were some problems with some cheapest journey searches. ATOC to send Carmen examples. |  | XML review meeting 24/10/05 |  |  | ATOC
O17 |  | Carmen to investigate issues from O16 |  | XML review meeting 24/10/05 |  |  | Carmen
O18 |  | Carmen to add enhancement to extra costs spreadsheet to allow a specification of a blanket time of closure for all tube transfers. |  | XML review meeting 24/10/05 |  |  | Carmen
O19 |  | Meeting needed between ATOC and Carmen to discuss what add-on functionality for fares is needed. |  | XML review meeting 24/10/05 |  |  | Carmen to organise.
O20 |  | Provide expected response times for the ArriveDepartRequest |  | XML review meeting 24/10/05 |  |  | Carmen
O21 |  | Suggest strategy for dealing with changes to the XML specification after the 25th November. |  | XML review meeting 24/10/05 |  |  | Frank
O22 |  | Apparently the RSID can get changed downstream somewhere. ATOC to follow up the implications of this. |  | XML review meeting 24/10/05 |  |  | ATOC

## XML Interface
ID | Due Date | Description | Last Update | Source | Summary Action | Status | Person | Findings
X1 |  | Carmen to add description of slow transfers calculation rule to the interface spec. |  | XML review meeting 24/10/05 |  |  | Carmen
X2 |  | Carmen to include OJP requirements in the XML design, (for example, generalise AvoidTube to be able to specify any type of transfer). ATOC would like the same XML to be used for both TrainPlanner and OJP. |  | XML review meeting 24/10/05 |  |  | Carmen
X3 |  | JourneyPlanningRequest - Station Messages - add severity, category and message ID attributes to each station message. |  | XML review meeting 24/10/05 |  |  | Carmen
X4 |  | JourneyPlanningResponse, DepartArriveResponse - Trips - Add Train Head Code. |  | XML review meeting 24/10/05 |  |  | Carmen
X5 |  | JourneyPlanningResponse - Trips - Add date of departure from train's origin. |  | XML review meeting 24/10/05 |  |  | Carmen
X6 |  | JourneyPlanningResponse - Routeing Guide - consider how to distingusih between normal routeing guide easement and bulletin easement and update XML as appropriate. |  | XML review meeting 24/10/05 |  |  | Carmen
X7 |  | ATOC will need a separate query for availability check (i.e. not just able to be done within a journey planning request). Carmen to investigate what is involved and determine if extra cost involved. Update XML as appropriate. |  | XML review meeting 24/10/05 |  |  | Carmen
X8 |  | ATOC to send information about extra fields required for bulletins so that TrainPlanner can read the message when a bulletin URL is used. |  | XML review meeting 24/10/05 |  |  | ATOC
X9 |  | Carmen to investigate what is involved in including the above information from X8 and determine if extra cost is involved. Update XML as appropriate. |  | XML review meeting 24/10/05 |  |  | Carmen
X10 |  | All requests and responses should include both Tiploc and CRS for stations. |  | XML review meeting 24/10/05 |  |  | Carmen
X11 | 2005-10-28 | Carmen to provide document comparing the RTTI enquiry port and IPTIS XML interface. Justify omissions and include any questions if not sure about things. |  | XML review meeting 24/10/05 |  |  | Carmen
X12 |  | DepartArriveRequest - should allow tiploc or CRS to be specified. |  | XML review meeting 24/10/05 |  |  | Carmen
X13 |  | DepartArriveRequest - add cancellation code. |  | XML review meeting 24/10/05 |  |  | Carmen
X14 |  | DepartArriveResponse - add station messages. |  | XML review meeting 24/10/05 |  |  | Carmen
X15 |  | ATOC to provide quality of service algorithm to Carmen. |  | XML review meeting 24/10/05 |  |  | ATOC
X16 |  | Carmen to consider what is required to implement quality of service and determine if extra cost is involved and update XML as required. |  | XML review meeting 24/10/05 |  |  | Carmen
X17 |  | DEpartArriveRequest - add parameter to allow Trains, Station Messages or both to be returned. |  | XML review meeting 24/10/05 |  |  | Carmen
X18 |  | Add RTTI vias reference data to the IPTIS reference data specification |  | XML review meeting 24/10/05 |  |  | Carmen
X19 |  | TripRequest - add time to the FromStation and ToStation |  | XML review meeting 24/10/05 |  |  | Carmen
X20 |  | TripRequest - add Train Head Code, TOC and Time |  | XML review meeting 24/10/05 |  |  | Carmen
X21 |  | TripRequest - add other Trip identifiers also |  | XML review meeting 24/10/05 |  |  | Carmen